## Instructions
How to use this workbook
PURPOSE
Board Action Tracker — track board and committee actions, including evaluation actions, to closure.
HOW TO USE
• Enter % complete (blue) and status. RAG computes automatically (Closed or ≥67% green · 34-66% amber · <34% red).
EDITABLE ASSUMPTIONS
All fields editable; actions illustrative.
STANDARDS NOTE
Aligned to NCCG 2018, OECD Principles, King IV and ISO 37000 by name; no copyrighted standard text is reproduced. Confirm requirements against the current instruments and applicable regulation.

## Action Tracker
Board Action Tracker
Board Excellence Centre™ · Track board and committee actions to closure
Action ID | Action | Source | Owner | Raised | Due Date | % Complete | Status | RAG
BA-01 | Refresh board skills matrix | Board evaluation | Co. Secretary | 2026-01-15 | 2026-03-31 | 60 | In Progress | AMBER
BA-02 | Strengthen risk reporting to board | Risk committee | CRO | 2026-01-20 | 2026-04-30 | 40 | In Progress | AMBER
BA-03 | Update CEO succession plan | Nomination committee | Chair | 2026-02-01 | 2026-05-31 | 20 | In Progress | RED
BA-04 | Director development programme | Board evaluation | Co. Secretary | 2026-02-10 | 2026-06-30 | 10 | Not Started | RED
BA-05 | Improve board pack quality | Board evaluation | CFO | 2026-01-10 | 2026-03-15 | 80 | In Progress | GREEN
BA-06 | Board diversity plan | Nomination committee | Chair | 2026-02-15 | 2026-07-31 | 0 | Not Started | RED