## Close Calendar
Day | Activity | Owner | Predecessor | Status
WD-2 | Pre-close cut-off communications | Controller
WD-1 | Bank reconciliations | Treasury
WD+1 | Post all journals | GL Team | WD-1
WD+2 | Sub-ledger close (AR/AP/Inv) | Process Owners | WD+1
WD+3 | Intercompany match | Group Accounting | WD+2
WD+4 | FX revaluation | Treasury | WD+3
WD+5 | Trial balance review | Controller | WD+4
WD+6 | Management accounts draft | FP&A | WD+5
WD+7 | CFO review | CFO | WD+6
WD+8 | Board pack issued | CFO Office | WD+7