## Risk Register
Strategic Risk Register
Outliers Risk Management Centre™ · Strategic risk register
Risk ID | Category | Risk Description | Cause | Consequence | Risk Owner | Likelihood (1-5) | Impact (1-5) | Inherent Score | Inherent Rating | Existing Controls | Control Effectiveness | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Treatment Strategy | Action / Mitigation | Action Owner | Target Date | Status
SR-001 | Macroeconomic | Sustained high inflation compresses real margins | Macro environment | Margin & demand erosion | CFO | 4 | 4 |  |  | Pricing strategy; cost control | Partially Effective | 3 | 3 |  |  | Treat | Dynamic pricing & indexation | CFO | 2026-03-31 | In Progress
SR-002 | Market/Competitive | Loss of share to digital entrant | Disruption | Revenue decline | CEO | 3 | 4 |  |  | Differentiation strategy | Partially Effective | 2 | 3 |  |  | Treat | Digital transformation programme | COO | 2026-06-30 | Open
SR-003 | Regulatory/Political | Adverse policy change in key market | Political shift | Market access risk | Strategy | 2 | 4 |  |  | Scenario planning; advocacy | Partially Effective | 2 | 3 |  |  | Tolerate | Maintain scenario & contingency | Head of Strategy | 2026-05-31 | Open
SR-004 | Growth/M&A | Acquisition integration fails to deliver | Poor integration planning | Value destruction | CEO | 3 | 4 |  |  | Integration playbook | Not Tested | 2 | 3 |  |  | Treat | Stand up integration office | CFO | 2026-04-30 | Open

## Taxonomy & Lists
Risk Category | Definition
Market/Competitive | Competitor, demand and market-shift risks
Business Model | Obsolescence and disruption of the model
Macroeconomic | Inflation, FX, rates and growth risks
Regulatory/Political | Policy, political and regulatory shifts
Reputational | Brand and stakeholder-trust risks
Growth/M&A | Expansion, M&A and integration risks
Innovation/Technology | Disruptive technology and AI risks
Talent/Capability | Capability to execute the strategy

## Summary
Strategic Risk Register — Summary
Auto-calculated from the Risk Register
Inherent rating | Count
Critical
High
Medium
Low
Open actions
Overdue actions

## Instructions
How to use this template
PURPOSE
Strategic Risk Register — a live register to identify, assess, treat and monitor risk.
HOW TO USE
• Add one row per risk on the Risk Register sheet. Use the Category drop-down (from Taxonomy & Lists).
• Score Likelihood (1-5) and Impact (1-5). Inherent Score (L×I) and Rating colour automatically.
• Record existing controls and rate Control Effectiveness; then score Residual Likelihood/Impact after controls.
• Choose a Treatment Strategy (Treat / Tolerate / Transfer / Terminate) and log the action, owner, target date and status.
• The Summary sheet tallies ratings and open/overdue actions automatically.
SCORING BANDS
Critical 15-25 · High 9-14 · Medium 4-8 · Low 1-3
GOVERNANCE
• 1st line (owners) maintain the register; 2nd line (risk) reviews; 3rd line (audit) assures.
• Escalate Critical/High residual risks and overdue actions to the Risk Committee.
DISCLAIMER
A management tool. Calibrate scoring scales and appetite to your organisation.