## Instructions
How to use this workbook
PURPOSE
Control Deficiency Tracker — log control deficiencies and track remediation to closure.
HOW TO USE
• One row per deficiency, linked to a control ref. Set severity and record root cause and remediation.
• Enter % complete (blue). RAG computes automatically (Closed or ≥67% green · 34-66% amber · <34% red).
• Severity colours automatically (Material/Significant/Moderate/Minor).
EDITABLE ASSUMPTIONS
All fields editable; sample deficiencies are illustrative.
GOVERNANCE
Reviewed by management and reported to the audit committee; material/significant deficiencies escalated.

## Deficiency Tracker
Control Deficiency Tracker
Internal Control Centre™ · Track and remediate control deficiencies
Def ID | Control Ref | Deficiency | Source | Severity | Root Cause | Remediation Action | Owner | Due Date | % Complete | Status | RAG
DEF-01 | FC-03 | Close checklist sign-offs incomplete | Internal Audit | Significant | Manual process; no system enforcement | Implement close-control workflow | Financial Controller | 2026-04-30 | 40 | In Progress | AMBER
DEF-02 | PR-05 | Three-way match overrides not reviewed | Controls Assessment | Significant | No exception review | Add exception review and reporting | AP Manager | 2026-03-31 | 60 | In Progress | AMBER
DEF-03 | IT-02 | Privileged access not fully logged | ITGC Review | Material | Logging not enabled on all systems | Enable and monitor privileged logging | IT Security | 2026-05-31 | 20 | In Progress | RED
DEF-04 | FA-04 | Asset verification overdue | Internal Audit | Moderate | Resource constraints | Schedule and resource verification | Finance | 2026-06-30 | 10 | Not Started | RED
DEF-05 | RA-05 | Revenue leakage analytics not run | Controls Assessment | Moderate | Tooling not deployed | Deploy revenue-assurance analytics | Revenue Assurance | 2026-07-31 | 0 | Not Started | RED