## Risk Register
Operational Risk Register
Outliers Risk Management Centre™ · Operational risk register
Risk ID | Category | Risk Description | Cause | Consequence | Risk Owner | Likelihood (1-5) | Impact (1-5) | Inherent Score | Inherent Rating | Existing Controls | Control Effectiveness | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Treatment Strategy | Action / Mitigation | Action Owner | Target Date | Status
OR-001 | Process | Payment processing error causes duplicate disbursement | Manual process; no maker-checker | Financial loss | Finance Ops | 3 | 3 |  |  | Dual authorisation | Partially Effective | 2 | 2 |  |  | Treat | Automate payment controls | FC | 2026-03-15 | In Progress
OR-002 | Systems | Core ERP outage halts operations | Ageing infrastructure | Downtime; revenue loss | IT | 2 | 4 |  |  | Redundancy; DR plan | Partially Effective | 2 | 3 |  |  | Treat | Test DR failover quarterly | IT Manager | 2026-02-28 | Open
OR-003 | People | Key-person dependency in treasury | No documented succession | Disruption on departure | HR | 3 | 3 |  |  | Cross-training | Ineffective | 2 | 3 |  |  | Treat | Document procedures; cross-train | Treasurer | 2026-04-30 | Open
OR-004 | Health & Safety | Workplace injury in warehouse | Inadequate PPE compliance | Injury; liability | Operations | 2 | 4 |  |  | Safety policy; PPE | Partially Effective | 1 | 3 |  |  | Treat | Safety audit & training | HSE Lead | 2026-03-31 | Open

## Taxonomy & Lists
Risk Category | Definition
Process | Failed or inadequate internal processes
People | Human error, capacity, key-person
Systems | IT system failure or unavailability
External Events | External disruptions and hazards
Fraud | Internal/external fraud
Third-Party | Vendor/outsourcing failure
Health & Safety | Workplace safety incidents
Data/Privacy | Data loss or privacy breach

## Summary
Operational Risk Register — Summary
Auto-calculated from the Risk Register
Inherent rating | Count
Critical
High
Medium
Low
Open actions
Overdue actions

## Instructions
How to use this template
PURPOSE
Operational Risk Register — a live register to identify, assess, treat and monitor risk.
HOW TO USE
• Add one row per risk on the Risk Register sheet. Use the Category drop-down (from Taxonomy & Lists).
• Score Likelihood (1-5) and Impact (1-5). Inherent Score (L×I) and Rating colour automatically.
• Record existing controls and rate Control Effectiveness; then score Residual Likelihood/Impact after controls.
• Choose a Treatment Strategy (Treat / Tolerate / Transfer / Terminate) and log the action, owner, target date and status.
• The Summary sheet tallies ratings and open/overdue actions automatically.
SCORING BANDS
Critical 15-25 · High 9-14 · Medium 4-8 · Low 1-3
GOVERNANCE
• 1st line (owners) maintain the register; 2nd line (risk) reviews; 3rd line (audit) assures.
• Escalate Critical/High residual risks and overdue actions to the Risk Committee.
DISCLAIMER
A management tool. Calibrate scoring scales and appetite to your organisation.