## Transformation Roadmap
Finance Transformation Roadmap Tracker
CFO Excellence Centre™ · Track transformation initiatives & benefits (editable)
Init ID | Initiative | Workstream | Owner | Start | End | % Complete | Benefit (₦m) | Status | RAG
FT-01 | Close optimisation | Controls | Controller | 2026-01-01 | 2026-04-30 | 60 | 15 | In Progress | AMBER
FT-02 | Rolling forecast rollout | FP&A | Head of FP&A | 2026-02-01 | 2026-06-30 | 40 | 20 | In Progress | AMBER
FT-03 | Reporting automation | Reporting | Finance Systems | 2026-01-15 | 2026-07-31 | 30 | 25 | In Progress | RED
FT-04 | Working capital programme | Cash | Treasury | 2026-03-01 | 2026-09-30 | 15 | 40 | Not Started | RED
FT-05 | ERP / EPM upgrade | Technology | CFO/IT | 2026-04-01 | 2026-12-31 | 5 | 30 | Not Started | RED
FT-06 | Finance capability uplift | People | CFO/HR | 2026-02-01 | 2026-10-31 | 25 | 10 | In Progress | RED
[6 empty] | 29 | 140

## Instructions
How to use this workbook
PURPOSE
Finance Transformation Roadmap Tracker — track transformation initiatives, progress and benefits.
HOW TO USE
• One row per initiative. Enter % complete and benefit (blue). RAG computes from progress/status.
• RAG: Complete or ≥67% green · 34-66% amber · <34% red. Total benefit and average progress compute automatically.
EDITABLE ASSUMPTIONS
All fields editable; add initiatives and workstreams as needed.
NOTE
Figures are illustrative placeholders.