## Risk Register
Enterprise Risk Register
Outliers Risk Management Centre™ · Enterprise-wide risk register
Risk ID | Category | Risk Description | Cause | Consequence | Risk Owner | Likelihood (1-5) | Impact (1-5) | Inherent Score | Inherent Rating | Existing Controls | Control Effectiveness | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Treatment Strategy | Action / Mitigation | Action Owner | Target Date | Status
ER-001 | Financial | Currency depreciation erodes margin on imported inputs | High FX exposure on COGS | Margin compression; covenant pressure | CFO | 4 | 4 |  |  | FX policy; partial forward cover | Partially Effective | 3 | 3 |  |  | Treat | Implement hedging policy to 70% cover | Treasurer | 2026-03-31 | In Progress
ER-002 | Technology/Cyber | Ransomware disrupts core systems | Phishing; unpatched systems | Operational outage; data loss | CISO | 3 | 5 |  |  | EDR; backups; awareness training | Partially Effective | 2 | 4 |  |  | Treat | Complete IR plan & tabletop test | CISO | 2026-02-28 | Open
ER-003 | Strategic | Disruptive competitor erodes market share | New low-cost entrant | Revenue decline | CEO | 3 | 4 |  |  | Strategy review; differentiation | Effective | 2 | 3 |  |  | Treat | Accelerate product roadmap | COO | 2026-06-30 | Open
ER-004 | Compliance/Legal | Non-compliance with new regulation | Regulatory change; weak monitoring | Penalties; licence risk | Compliance | 3 | 4 |  |  | Obligations register; monitoring | Partially Effective | 2 | 3 |  |  | Treat | Stand up regulatory-change process | Head of Compliance | 2026-04-30 | Open
ER-005 | Fraud/Financial Crime | Procurement fraud via vendor collusion | Weak segregation; override | Financial loss; reputational | CFO | 3 | 3 |  |  | Vendor vetting; approvals | Partially Effective | 2 | 2 |  |  | Treat | Deploy anti-fraud analytics | Internal Audit | 2026-05-31 | Open

## Taxonomy & Lists
Risk Category | Definition
Strategic | Risks to strategy, business model and value creation
Financial | Liquidity, credit, market, capital and reporting risks
Operational | Process, people, systems and external-event risks
Compliance/Legal | Regulatory, legal and conduct risks
Technology/Cyber | Cyber, data, AI and technology risks
People/HR | Talent, key-person, culture and conduct risks
Third-Party | Vendor, supplier and outsourcing risks
Reputational | Brand, stakeholder and trust risks
ESG/Climate | Environmental, social, governance and climate risks
Fraud/Financial Crime | Internal/external fraud, bribery and corruption

## Summary
Enterprise Risk Register — Summary
Auto-calculated from the Risk Register
Inherent rating | Count
Critical
High
Medium
Low
Open actions
Overdue actions

## Instructions
How to use this template
PURPOSE
Enterprise Risk Register — a live register to identify, assess, treat and monitor risk.
HOW TO USE
• Add one row per risk on the Risk Register sheet. Use the Category drop-down (from Taxonomy & Lists).
• Score Likelihood (1-5) and Impact (1-5). Inherent Score (L×I) and Rating colour automatically.
• Record existing controls and rate Control Effectiveness; then score Residual Likelihood/Impact after controls.
• Choose a Treatment Strategy (Treat / Tolerate / Transfer / Terminate) and log the action, owner, target date and status.
• The Summary sheet tallies ratings and open/overdue actions automatically.
SCORING BANDS
Critical 15-25 · High 9-14 · Medium 4-8 · Low 1-3
GOVERNANCE
• 1st line (owners) maintain the register; 2nd line (risk) reviews; 3rd line (audit) assures.
• Escalate Critical/High residual risks and overdue actions to the Risk Committee.
DISCLAIMER
A management tool. Calibrate scoring scales and appetite to your organisation.