## AI Risk Register
AI Risk Register
Outliers Data & AI Centre™ · Identify, assess and treat AI system risk
Risk ID | AI System / Use Case | Risk Category | Risk Description | Cause | Potential Impact | Risk Owner | Likelihood (1-5) | Impact (1-5) | Inherent Score | Inherent Rating | Existing Controls | Control Effectiveness | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Treatment | Mitigation Action | Action Owner | Target Date | Status
AIR-001 | Credit scoring model | Bias & Fairness | Model produces biased decisions across protected groups | Unrepresentative training data | Discrimination; regulatory & reputational harm | Head of Data Science | 4 | 4 | 16 | Critical | Fairness testing; human review | Partially Effective | 2 | 3 | 6 | Medium | Treat | Implement bias monitoring & reweighting | ML Lead | 2026-03-31 | In Progress
AIR-002 | Customer chatbot (GenAI) | Accuracy / Hallucination | LLM generates incorrect or fabricated answers | Model limitations; weak grounding | Customer harm; misinformation | Product Owner | 4 | 3 | 12 | High | RAG grounding; disclaimers | Partially Effective | 3 | 2 | 6 | Medium | Treat | Add retrieval grounding & guardrails | AI Eng | 2026-02-28 | In Progress
AIR-003 | Fraud detection model | Model Drift | Performance degrades as patterns change | No drift monitoring | Missed fraud; losses | Risk Analytics | 3 | 4 | 12 | High | Periodic retraining | Ineffective | 2 | 3 | 6 | Medium | Treat | Deploy drift monitoring & alerts | MLOps | 2026-04-30 | Open
AIR-004 | Document AI (PII) | Data Privacy | Personal data exposed via model or logs | Weak data handling | Privacy breach (NDPA) | DPO | 3 | 5 | 15 | Critical | Access controls; masking | Partially Effective | 2 | 4 | 8 | Medium | Treat | PII redaction & retention controls | Security Eng | 2026-03-15 | Open
AIR-005 | Vendor LLM API | Third-Party / Security | Sensitive data sent to external model provider | No data-handling agreement | Data leakage; compliance | CISO | 3 | 4 | 12 | High | Vendor review; no-train clause | Partially Effective | 2 | 3 | 6 | Medium | Treat | Data-loss prevention on prompts | Security | 2026-05-31 | Open

## Instructions
How to use this template
PURPOSE
AI Risk Register — identify, assess, treat and monitor risks specific to AI/ML systems and use cases.
HOW TO USE
• One row per AI system or use case risk. Pick a Risk Category from the drop-down.
• Score Likelihood and Impact (1-5). Inherent Score (L×I) and Rating colour automatically.
• Record controls and effectiveness, then score residual L×I after controls.
• Choose a treatment and log mitigation, owner, target date and status.
SCORING BANDS
Critical 15-25 · High 9-14 · Medium 4-8 · Low 1-3
GOVERNANCE
Model owners assess; second-line AI risk oversees; AI Governance Committee and board receive reporting.
NOTE
Calibrate scoring and categories to your AI governance policy. Confirm privacy items against NDPA.